| CODEVMET-AFI Project revised budget for 2025 Note: All amounts in this paper are given in United States Dollars |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Total | Round up 500 | 2016-2022 | 2023 | 2024 | 2025 | 2026 |
| Expenditures | 344 473 |  | 52 187 | 43 157 | 56 629 | 175 000 | 17 500 |
| Recapitulation | 104 696 | 184 500 | 38 904 | 71 609 | 86 705 | 175 000 | 15 000 |
| Submission action plans - Project documentation - On request services | 171 648 | - | 30 334 | 64 109 | 64 205 | 13 000 | - |
| Objective 1: Assist AFI States in the enhancement of the capability of their regulatory authority in carrying out safety oversight of MET service and the implementation of QMS in MET | 45 824 |  | 15 167 | 30 657 |  |  |  |
| Deliverable 1.1: Generic regulations, guidance material, operational procedures, technical tools, QMS related guidance and procedures | 45 824 |  | 15 167 | 30 657 |  |  |  |
| Deliverable 1.2: Submission of States’ plans of actions, monitoring and assistance of the implementation activities related to MET safety oversight and QMS implementation | 0 |  |  |  |  |  |  |
| Activity 1.2.3: Conduct "On request" specific seminars or workshops […] | 177 452 |  |  | 2 795 |  |  |  |
| Activity 1.2.6: Corrective Action Plan (CAP) implementation assistance mission to recipient States (Assistance missions to States) | 51 205 |  |  |  | 51 205 |  |  |
| Activity 1.2.7: Conduct a 5-day training of QMS internal auditors | 26 000 |  |  |  | 13 000 | 13 000 |  |
| Project Implementation package for AMET-B1 elements | 30 816 | 31 000 |  |  | - | 31 000 | - |
| 3.2 Conduct onsite validation workshop (in Dakar, Senegal) to review and validate AMET-B1 generic implementation documentation | 30 816 | 31 000 |  |  |  | 31 000 |  |
| Assistance to States in CAP implementation | 31 068 | 43 000 | - | - | - | 43 000 | - |
| 4.1 Assist The Gambia in CAP development | 10 863 | 11 000 |  |  |  | 11 000 |  |
| 4.2 Assist Gabon on CAP development | 12 123 | 12 500 |  |  |  | 12 500 |  |
| 4.3 Assist ASECNA in CAP Implementation (Lomé, Togo) | 8 082 | 8 500 |  |  |  | 8 500 |  |
| 4.4 Assist Nigeria in in developing a CAP for implementing ASBU elements in the MET area | 10 821 | 11 000 |  |  |  | 11 000 |  |
| Wrap-up visits to States | 16 398 | 16 500 |  |  |  | 16 500 |  |
| 5.1 Follow-up visit to Cabo Verde | 5 466 | 5 500 |  |  |  | 5 500 |  |
| 5.2 Follow-up visit to Cameroon | 5 466 | 5 500 |  |  |  | 5 500 |  |
| 5.3 Follow-up visit to Côte d'Ivoire | 5 466 | 5 500 |  |  |  | 5 500 |  |
| Capacity building | 12 123 | 12 500 |  |  | - | 12 500 | - |
| 6.1 Quality Internal Auditors training (Yaoundé, CCAA School) | 12 123 | 12 500 |  |  |  | 12 500 |  |
| Update the AMBEX Handbook and the ICD | 30 658 | 31 000 |  |  | - | 31 000 | - |
| 8.1 Onsite workshop on the updating of AMBEX Handbook and the ICD (Dakar, Senegal) | 28 408 | 28 500 |  |  |  | 28 500 |  |
| Catering (5 days coffee and lunch for 15 participants) | 2 250 | 2 500 |  |  |  | 2 500 |  |
| Steering Committee Meetings | 66 911 | 67 000 | 8 570 | 7 500 | 22 500 | 13 500 | 15 000 |
| SC/1(Dakar) | 521 |  | 521 |  |  |  |  |
| SC/2 (Virtual) |  |  |  |  |  |  |  |
| SC/3 (Yaoundé) | 8 049 |  | 8 049 |  |  |  |  |
| SC/4 (Freetown) | 7 500 | 7 500 |  | 7 500 |  |  |  |
| SC/5 (WACAF) | 22 500 | 22 500 |  |  | 22 500 |  |  |
| SC/6 (ESAF) | 13 341 | 13 500 |  |  |  | 13 500 |  |
| SC/7 (WACAF) | 15 000 | 15 000 |  |  |  |  | 15 000 |
| Sundry | 3 530 | 3 530 | 371 | 383 | 276 | 1 500 | 1 000 |
| Overhead charges | 2 000 | 2 000 | 4 728 | 3 674 | 5 148 | 3 000 | 1 500 |
| Contributions | 333 473 | 190 030 | 173 731 | 24 128 | 65 818 | 35 000 | 34 796 |
| Annual membership fees | 333 473 |  | 119 523 | 24 128 | 65 818 | 62 002 | 62 002 |
| Total | - | 190 030 | 80 619 | 51 538 | 26 311 | 144 500 | 44 502 |