Fifth Meeting of the Steering Committee (SC/5) of the CODEVMET-AFI Project, Abidjan, Côte d’Ivoire, 30 September to 2 October 2024

Summary of SC/5 Decisions

SC/5 Decision 5/01 – Resolution of Longstanding MET Issues in States

That, to strengthen the safety and reliability of meteorological services in support of aviation, States and Organizations to leverage on the project as a primary mechanism for implementing the MET related SARPs and addressing outstanding aeronautical meteorology (MET) challenges in the region.

SC/5 Decision 5/02 – Payment of annual contributions to the project

That to improve the financial situation of the project, the Secretariat to,

- include an installment payment proposal in the letters requesting contributions to facilitate the smooth settlement of longstanding arrears;

- explore additional funding sources for the project through donors and financial institutions; and

- establish an ad hoc group to develop by 31 May 2025, a proposal for a mechanism to encourage States/Organizations to join and contribute to the project.

SC/5 Decision 5/03 – Overcoming the challenges faced by the Project

That to increase the effectiveness of the project,

- ICAO ESAF and WACAF Regional Offices to encourage their States of accreditation to effectively participate in the project; and

- The Secretariat to define a mechanism for updating the Project implementation packages;

- The Secretariat to coordinate the incorporation of the recent amendments of Annex 3 to Chicago Convention in the Project implementation documentation by 30 June 2025; and

- The Secretariat to update the list of State focal points for the CODEVMET-AFI project and organize briefing meetings with them on the project and the scope of their mandate.

SC/5 Decision 5/04 – Implementation of the Project objectives

That to facilitate the implementation of the Project objectives,

- The terms of reference of the project teams are approved as provided in Appendices 5, 6, 7 and 8; and

- The Secretariat to coordinate the establishment of the project teams by 31 March 2025 and supports their work.

SC/5 Decision 5/05 – Coordination with AAMAC within the framework of the CODEVMET-AFI project

That to reinforce the synergy of actions between the African and Malagasy Civil Aviation Authorities (AAMAC) and the CODEVMET project,

- The African and Malagasy Civil Aviation Authorities should:

- participate in the development and updating of generic MET documentation to avoid duplication of efforts; and

- participate in the project implementation activities.

- The Secretariat to explore the possibilities of establishing an agreement with AAMAC within the framework of the CODEVMET-AFI Project.

SC/5 Decision 5/06 – Project work plan for 2024/2025

That the project work plan for 2024/2025 is endorsed as provided in Appendix 9.

SC/5 Decision 5/07 – Follow-up on the progress of project implementation

That to ensure the effective implementation of the planned activities, the steering committee to hold a mid-term meeting to monitor the progress and provide guidance as appropriate.

SC/5 Decision 5/08 – CODEVMET-AFI Project budget for 2024/2025

The project budget for 2024/2025 is approved as provided in Appendix 10 to this report.

SC/5 Decision 5/09 – Venue and date of the next steering committee meeting

The Federal Republic of Nigeria offered to host the next Steering committee meeting in 2025. The Secretariat to coordinate with Nigeria for the organization of the sixth meeting of the CODEVMET-AFI Project steering committee (SC/6) by 30 June 2025.