.

Appendix 4 – Status of implement of the Codevmet planned activities for 2023/2024

| Activity # | Activity Name | Status | Outcomes /Achivements | Beneficiary States/ANSPs | Date of completion | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1 | Assist States in the enhancement of the capability their regulatory authority in carrying out safety oversight of MET service and the implementation of QMS in MET |  |  |  |  |  |
| Deliverable 1.1 | Generic regulations, guidance material, operational procedures, technical tools, QMS related guidance and procedures | Completed | • QMS implementation packages developed and validated • MET Safety Regulatory Implementation package developed and validated | Project recipient States | 5-9 Sep. 2022 | Packages validated through "Validation workshops" |
| Deliverable 1.2 | Submission of States Plans of actions, monitoring and assistance of the implementation activities related to MET safety oversight and QMS implementation | Ongoing |  |  |  |  |
| 1.2.1 | Submit to ICAO, for review, action plans for the improvement of safety oversight of MET services and for the implementation of the QMS in MET | Completed | Six (6 States) submitted their CAP on QMS and MET Safety | Botswana, Cameroon, Cabo Verde, Côte d'Ivoire, Gambia, Togo | March 2023 - March 2024 |  |
| 1.2.2. | Monitor progress in the implementation of action plans by States in the framework of improvement State’s safety oversight of MET services and the implementation of the QMS in MET |  |  |  |  |  |
| 1.2.2.1 | Monitor progress in the implementation of State corrective action plans related to State’s safety oversight capacity of MET services | Completed | Progress reports provided by Experts | Botswana, Cameroon, Cabo Verde, Côte d'Ivoire, Gambia, Togo | March 2023 - Sep. 2024 |  |
| 1.2.2.1 | Monitor progress in the implementation of State action plans related to State MET Service Provider QMS in MET | Completed | Progress reports provided by Experts | Botswana, Cameroon, Cabo Verde, Gambia, Togo | March 2023 - Sep. 2024 |  |
| 1.2.3. | Conduct ''On request'' Specific seminars /workshops for a State or group of States or in the initiative of ICAO EASF and WACAF Regional Offices to address specific performance issues within the framework of the implementation of the project | Completed |  |  |  |  |
| 1.2.3.1 | Assist Gambia CAA and Gambia MET Service Provider to train Aeronautical Meteorological Personnel Competence Assessors | Completed | Ten (10) MET staffs trained as aeronautical meteorological personnel competency assessors | Gambia | 14 - 29 Dec. 2023 |  |
| 1.2.4 | Conduct of a 3-day English workshop (one day dedicated to the implementation of MET oversight activities and two days on the management of the processes (Online)) | Completed | Report on the Workshop on the management of QMS processes | Botswana; Cabo Verde; Gambia; Nigeria; Seychelles and Sierra Leone | 27 June 2023 | The following non-participating States attended the workshops: Angola; Burundi; Burkina Faso; Chad; Comoros; Congo; Eritrea; Eswatini; Ethiopia; Ghana; Guinea; Kenya; Liberia; Madagascar; Mali; Mauritius; Namibia; Rwanda; Sao Tome and Principe; South Africa; Tanzania |
| 1.2.5 | Conduct of a 3-day French workshop (one day dedicated to the implementation of MET oversight activities and two days on the management of the QMS processes (Online)) | Completed | Report on the Workshop the management of the QMS processes | Benin; Cameroon; Côte d'Ivoire; Gabon; Niger; Senegal; Togo and ASECNA | 17 July 2023 |  |
| 1.2.6 | Codevmet Project Corrective Action Plan (CAP) related to the QMS and MET Safety Oversight Implementation assistance mission to recipient States | Ongoing |  |  |  |  |
| 1.2.6.1 | Assistance mission to Botswana on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Not started | Not completed, as State doesn't confirm their willing to be assisted. |  |  |  |
| 1.2.6.2 | Assistance mission to Cabo Verde on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Completed | • MET Safety CAP • QMS CAP | Cabo Verde | 13 - 17 May 2024 |  |
| 1.2.6.3 | Assistance mission to Cameroon on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Completed | • MET Safety CAP • QMS CAP | Cameroon | 8 - 12 July 2024 |  |
| 1.2.6.4 | Assistance mission to Côte d’Ivoire on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Completed | MET Safety CAP | Côte d'Ivoire | 3 - 7 June 2024 |  |
| 1.2.6.5 | Assistance mission to Gambia in the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Ongoing | • Remote assistance on CAP review provided to State • Onsite assistance mission still under coordination with State | The Gambia | May 2024 |  |
| 1.2.6.6 | Assistance mission to Senegal on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Completed | QMS CAP | Senegal | 2 - 6 Sep. 2024 |  |
| 1.2.6.7 | Assistance mission to Togo on the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ and MET Safety Oversight | Completed | • MET Safety CAP • QMS CAP | Togo | 10 - 14 June 2024 |  |
| 1.2.6.8 | Assistance mission to ASECNA (Congo) the implementation of the Codevmet Project Corrective Action Plan (CAP) related to the SMQ | Ongoing | • ASECNA CAP was approved • Coordination with ASECNA on CAP implementation ongoing. | ASECNA | 8 Apr. 2024 |  |
| 1.2.7 | Conduct a 5-day training of QMS internal auditors | Not started | - | - | - | The completion of this action depends on the progress in the implementation of QMS CAP |
| 1.2.8 | Provide quarterly and end of mission/activity reports on the implementation of the Project Corrective Action Plan (CAP) related to QMS and MET Safety Oversight | Completed | Missions Reports on Project assistance to States | Assisted States and WACAF Office | May to Sep. 2024 |  |
| Objective 2. | Establishment of a pool of competent subject-matter experts (SMEs) to carry out project activities |  |  |  |  |  |
| Deliverable 2.1 | Project expert teams (SME) updated, and tasks assigned | Completed |  |  |  |  |
| 2.1.1 | Update project experts by selecting SMEs to serve as project experts | Completed | CNS and MET SME selected | ESAF and WACAF States provided experts | Apr. 2024 |  |
| 2.1.2 | Train selected SMEs on the project methodology and assign tasks | Completed | Selected CNS and MET SME trained on the Project methodology | ESAF and WACAF States provided experts | May 2024 |  |
| 2.1.3 | Assign tasks to the Project SMEs with regards to the project objectives | Completed | Working Groups were established and tasks assigned | ESAF and WACAF States provided experts | May 2024 |  |
| Deliverable 2.2 | Project Work Plans reviewed and approved, including steering committee meetings | Ongoing |  |  |  |  |
| 2.2.1 | Develop a detailed project work plans on the annual basis including a detailed schedule containing all the activities that need to be undertaken as part of the project. | Completed | The 2023/2025 Work plan | Recipient States/Organizations | Sep. 2024 |  |
| 2.2.2 | Submit and present the project work plans to the Steering Committee | Completed | The 2023/2025 Work plan is under development | Recipient States/Organizations | Sep. 2024 |  |
| 2.2.3 | Approval of the work plans. | Ongoing | Work plan to be submitted to the SC/5 Meeting under preparation | SC Member States/Organizations | 30 Sep. - 2 Oct. 2024 |  |
| Objective 3. | Conduct data collection on the current status of AMET-B1/1, AMET-B1/2 and AMET-B1/4 at the State MET service provider |  |  |  |  |  |
| Deliverable 3.1 | Documented data on the status of the scoped AMET-B1 elements at States MET Service providers | Not started |  |  |  |  |
| 3.1.1 | Collect data on the current status of the scoped AMET-B1 elements at the MET service provider | Not started |  |  |  |  |
| 3.1.2 | Organize and categorize collected data per enabler related to the scoped AMET-B1 elements | Not started |  |  |  |  |
| Objective 4. | Develop generic documentation required to implement the project activities |  |  |  |  |  |
| Deliverable 4.1 | Implementation packages of the scoped AMET-B1 elements | Not started |  |  |  |  |
| 4.1.1 | Conduct a meeting to determine the list of generic implementation documents of the scoped AMET-B1 elements | Not started |  |  |  |  |
| 4.1.2 | Develop generic documentation required for effective implementation of the scoped AMET-B1 elements, including generic regulations, procedures, training material, technical guidance related the infrastructure and systems, etc. | Not started |  |  |  |  |
| 4.1.3 | Conduct onsite validation workshop on the implementation packages of the scoped AMET-B1 elements | Not started |  |  |  |  |