## Codev Project 2025 Schedule
CODEVMET-AFI Project : Work Plan for 2024/2025
START DATE
2024-01-01
[7 empty] | 2024-01-01 | [11 empty] | 2025-01-01 | [11 empty] | 2026-01-01 | [11 empty] | 2027-01-01 | [11 empty] | 2028-01-01 | [11 empty] | 2029-01-01 | [11 empty] | DO NOT ALTER CELL BELOW
[7 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y4Q1 |  |  | Y4Q2 |  |  | Y4Q3 |  |  | Y4Q4 |  |  | Y5Q1 |  |  | Y5Q2 |  |  | Y5Q3 |  |  | Y5Q4 |  |  | Y5Q1 |  |  | Y5Q2 |  |  | Y5Q3 |  |  | Y5Q4
Activity # | Project Tasks | Level | Resources | Start Dtate | End Dtae | # of Days | [72 empty] | 2029-01-01 | time axis 2024-01-01 to 2029-12-01
 | time axis 2024-01-01 to 2029-12-01
1. | Assitance to Cabo Verde, Cameroon, Côte d'Ivoire; Senegal; Togo | L3 |  | 2024-01-01 | 2024-10-02 | 198 | bar: 2024-01-01 to 2029-12-01
1.1 | Assistanace misions on MET Safety and QMS CAPs implementation |  | 4 | 2024-01-01 | 2024-09-30 | 196 | bar: 2024-01-01 to 2024-09-01
1.2 | Daft project 2024/2025 work plan |  | 1 | 2024-09-18 | 2024-09-30 | 9 | bar: 2024-09-01; 2024-11-01 to 2024-12-01
1.3 | Submit the project work plan to the Fourth Steering Committee Meeting (SC/4) for approval |  | 1 | 2024-09-30 | 2024-10-02 | 3 | bar: 2024-09-01 to 2024-12-01
2 | AMET-B1 Current Status in Recipient States | L3 |  | 2025-02-03 | 2025-07-31 | 129 | bar: 2024-01-01 to 2029-12-01
2.1 | Gather data on AMET-B1 status in the recipient States |  | 6 | 2025-02-03 | 2025-04-30 | 63 | bar: 2024-11-01 to 2024-12-01; 2025-02-01 to 2025-04-01
2.2 | Review, analyse collected data and provide reports on the current status of AMET-B1 for each State |  | 6 | 2025-05-01 | 2025-06-30 | 43 | bar: 2024-11-01 to 2024-12-01; 2025-05-01 to 2025-06-01
2.3 | Approve reports on the current status of AMET-B1 for each State |  | 7 | 2025-07-01 | 2025-07-31 | 23 | bar: 2024-11-01 to 2024-12-01; 2025-07-01
3 | Project Implementation package for AMET-B1 elements | L3 |  | 2025-03-03 | 2025-11-28 | 195 | bar: 2024-01-01 to 2029-12-01
3.1 | Review and update the QMS and MET Safety Implementation Packages (online) |  | 6 | 2025-03-03 | 2025-06-30 | 86 | bar: 2024-11-01 to 2024-12-01; 2025-03-01 to 2025-06-01
3.2 | Develop project generic implementation documents related to AMET-B1 elements |  | 8 | 2025-07-01 | 2025-11-28 | 109 | bar: 2024-11-01 to 2024-12-01; 2025-07-01 to 2025-11-01
3.3 | Conduct onsite validation workshop (in Dakar, Senegal) to review and validate AMET-B1 generic implementation documentation |  | 8 | 2025-12-01 | 2025-12-05 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-12-01
4 | Assistance to Gambia, Gabon, Sierra Leone and ASECNA | L3 |  | 2025-04-07 | 2025-09-12 | 115 | bar: 2024-01-01 to 2029-12-01
4.1 | Assistance Mission to Gambia for developing a Corrective Action Plan (CAP) related to MET Safety and Quality Managment System |  | 3 | 2025-04-07 | 2025-04-11 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-04-01
4.2 | Assistance mission to Gabon for developing a CAP related to MET Safety and Quality Management Systems |  | 3 | 2025-06-02 | 2025-06-06 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-06-01
4.3 | Assistance mission to ASECNA on CAP implementation (Lomé, Togo) |  | 2 | 2025-09-08 | 2025-09-12 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-09-01
4.4 | Assistance to Nigeria in developing a CAP for implementing ASBU elements in the MET area |  | 3 | 2025-08-18 | 2025-08-22 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-08-01
4.5 | Assistance mission to Sierra Leone for developing a CAP for MET Safety and Quality Management Systems (QMS) |  | 3 | 2025-05-19 | 2025-05-23 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-05-01
5 | Follow-up visits to States | L3 |  | 2025-05-05 | 2025-08-13 | 73 | bar: 2024-01-01 to 2029-12-01
5.1 | Follwow-up mission to Cabo Verde |  | 2 | 2025-05-05 | 2025-05-09 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-05-01
5.2 | Follwow-up mission to Cameroon |  | 2 | 2025-06-09 | 2025-06-11 | 3 | bar: 2024-11-01 to 2024-12-01; 2025-06-01
5.3 | Follwow-up mission to Côte d'Ivoire |  | 2 | 2025-08-11 | 2025-08-13 | 3 | bar: 2024-11-01 to 2024-12-01; 2025-08-01
6 | Capacity building | L3 |  | 2025-08-18 | 2025-08-22 | 5 | bar: 2024-01-01 to 2029-12-01
6.1 | Quality Internal Auditors training, Yaoundé, CCAA School |  | 3 | 2025-08-18 | 2025-08-22 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-08-01
7 | Sixth Steering Committee meeting | L3 |  | 2025-09-28 | 2025-10-01 | 3 | bar: 2024-01-01 to 2029-12-01
7.1 | Sixth Meeting of the Steering Committee (SC/6) |  | 3 | 2025-09-28 | 2025-10-01 | 3 | bar: 2024-11-01 to 2024-12-01
8 | Update AMBEX Handbook and the ICD | L3 |  | 2025-12-08 | 2026-06-13 | 135 | bar: 2024-01-01 to 2029-12-01
8.1 | Onsite workshop on the updating of AMBEX Handbook and the ICD (Dakar, Senegal) |  | 8 | 2025-12-08 | 2025-12-13 | 5 | bar: 2024-11-01 to 2024-12-01; 2025-12-01
8.2 | Develop the Draft Update of AMBEX Handbook and the ICD |  | 8 | 2026-01-01 | 2026-05-30 | 107 | bar: 2024-11-01 to 2024-12-01; 2026-01-01 to 2026-12-01
8.3 | Remote validation of the updated AMBEX Handbook and the ICD |  | 8 | 2026-06-08 | 2026-06-13 | 5 | bar: 2024-11-01 to 2024-12-01; 2026-01-01 to 2026-12-01