## State Data
RNAV to RNP Chart Identification Change
Regional Transition Plan Template | [7 empty] | To be used in conjunction with Circular 353 only
Region: | APAC
Circ. 353 Reference | 5.2.2 | 5.4.4.1 |  |  |  |  | 5.4.4.4 | [8 empty] | 5.4.4.3
State | Project Team Manager or designated focal point | Current number of RNAV Charts | Surveyed (as of 6 Jun 2018) | State response (AP051-18) Published | Planned | total | Does the volume of charts require clustering into smaller regions? | Sub region A | Number of Charts in A | Sub Region B | Number of Charts in B | Sub Region C | Number of Charts in C | Prioritization of the sub regions (where appropriate) | Proposed number of AIRAC cycles | Time required for planning and communication | Proposed start date for publication of new charts | Remarks/State's comment
Afghanistan |  | 6 | 3 |  |  | 0
Australia | Jacqueline Vials International Standards ¦ Aviation Environment Jacqueline.Vials@infrastructure.gov.au | 639 | 623 | 653 |  | 653 | No. but would consider any proposal from neighboring States | [7 empty] | 3 yrs (periodic review cycle) 18 months (resources available) | 3 to 6 months advance notice | At any time | At any time subject to a period of 3 to 6 months’ advanced notice for planning purposes and submission lead times Airservices would propose to leverage the triennial procedure revalidation cycle and make changes to most procedures at the time they are subject to periodic review An accelerated deployment would be possible, subject to additional resources being made available, which could possibly achieve the transition in 18 months Australian DAP is published quarterly, Airservices preference would to be to promulgate updated procedures only on these dates only and not a ‘regular’ AIRAC date
Bangladesh | Sabera Rahman mitasr@gmail.com | 1 | 6 | 1 |  | 1 | [11 empty] | 5 RNP, 1 RNAV(GNSS)
Bhutan |  | 3 | 0 | 0 | 0 | 0 | No | [7 empty] | 1 | 1 year |  | RNP AR cloud break procedure will be published with new chart title by Jul 2018 (tentatively)
Brunei Darussalam |  | 2 | 2 |  |  | 0
Cambodia |  | 5 | 5 |  |  | 0
China | Mr. Wang Bihe, Flight Operations Management Division, Flight Standards Department of CAAC, bh_wang@caac.gov.cn | 10 | 422 | 317 |  | 317 | No | [7 empty] | 30 |  | Oct 2018 | Transition period: 11 Oct 2018 - 31 Dec 2020 Published PBN approach procedures are in domestic AIP and will not affect regional transition.
Hong Kong, China | Ms. Jenny Lee jyylee@cad.gov.hk |  | 8 | 8 | 0 | 8 | Macao | [7 empty] | 6 | 12 AIRAC Cycle | 2020
Macao, China | Mr. Bryan, K.H. Chiu bryanchiu@aacm.gov.mo |  | 2 | 4 | 1 | 5 | Hong Kong | [7 empty] | 6 | 12 AIRAC cycle | 2020 | New one RNP (AR) procedure is planned.
Taipei FIR |  |  | 22 |  |  | 0
Cook Islands |  | 15 | 10 |  |  | 0
Democratic Peoples Republic of Korea | Mr. An Kyong Hwa gaca@silibank.com | 3 | 4 |  |  | 0
Fiji | ILAITIA TABAKAUCORO ilaitia.tabakaucoro@caaf.org.fj | 8 | 7 | 8 | 5 | 13 | No | [7 empty] | 1 |  | 8 Nov 2018 | Planned 2 GPS based approaches
India | Mr. A.K. Meena akmeena@aai.aero | 3 | 3 | 4 |  | 4
Indonesia | Mega Herdiyansya m3g4_666@yahoo.com | 76 | 57 |  |  | 0
Japan | Mr. Makito Oohashi oohashi-m07ys@mlit.go.jp | 127 | 108 | 93 | 0 | 93 | No | [7 empty] | TBD |  | TBD | Published 25 GPS based approaches. Planned to redesign GPS procedures to RNAV(GNSS), then begin to transition
Kiribati |  | 2 | 4 |  |  | 0
Lao Peoples' Democratic Republic | Sohnsacksit KHAMKEO saykhamkeo@gmail.com | 5 | 5 |  |  | 0
Malaysia | Mr. Nordian Ibrahim nordian@dca.gov.my | 50 | 45 |  |  | 50 | [8 empty] | 6 |  | Jan 2020
Maldives | Mr. Ibrahim Hameed i.hameed@macl.aero |  | 18 | 16 | 0 | 16 | No | [7 empty] | 1 | 1.5 AIRAC cycle | Oct 2018 | Published 4 GPS based approaches Transition began effective on Jan 2 2019
Marshall Islands |  | 6 | 2 |  |  | 0
Micronesia |  | 10 | 10 |  |  | 0
Mongolia | Ms. Zolzaya Yulen zolzaya@mcaa.gov | 3 | 1 |  |  | 0
Myanmar | Mr. Soe Paing ats@dca.gov.mm Soepng1@gmail.com | 1 | 0 | 0 | 0 | 0 | No | [7 empty] | NA | NA | NA
Nauru |  |  | 0 |  |  | 0
Nepal | Mr. Mahesh Kumar Basnet atsdr@caanepal.org.np; cnsatm@mos.com.np | 4 | 2 | 4 | 0 | 4 | No | [7 empty] | 2 |  | Mar 2019
New Zealand | Ray Harvey ray.harvey@caa.govt.nz | 148 | 136 | 126 | 10 | 136 | Neighboring States, i.e. Australia, New Caledonia, Fiji, Vanuatu, Tonga, Nuie, Samoa, Cook Islands, French Polynesia | [7 empty] | 5 years | 1 year | 2020 | Progressive changes in accordance with periodic maintenance schedule of 5 years. International aerodromes first. Prefer to integrate changes at international aerodromes with neighboring States Concerns on FMS acceptance and aerodromes which have RNP APCH and RNP AR APCH AIC and CAA Safety Promotion material will be published
Pakistan | Mr. Muhammad Aslam Awan Aslam.Awan@caapakistan.co.pk | 43 | 43 | 43 | 1 | 44 | No | [7 empty] | 12 |  | 01 Jan 2019
Palau |  | 2 | 2 |  |  | 0
Papua New Guinea |  | 2 | 16 |  |  | 0
Philippines | Mrs. Jessica Adeline D. Jamero jadjamero@caap.gov.ph jamerojessica@gmail.com | 33 | 33 | 31 | 10 | 41 | No | [7 empty] | 12 |  | 2020 | 12 AIRAC cycles in 3 years, completed by 20 Nov 2022 CAAP is transitioning to a new chart software in 2018. Migration of old charts to new system will be completed in 2019
Republic of Korea | Mr. Koh Hanseung koh119@korea.kr | 38 | 33 | 32 | 15 | 47 | No | [7 empty] | 1 |  | Mar 2019
Samoa |  | 5 | 5 |  |  | 0
Singapore | Mr. Michael Shee michael_shee@caas.gov.sg | 6 | 6 | 6 | 0 | 6 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 1 month prior to issuance of AIP supplements to inform of the new charts which would be effective in 2 AIRAC cycles | Anytime | Nil
Solomon Islands | Mr. Alfred Tannyson Pitaa apitaa@mca.gov.sb; ats@solomon.com.sb |  | 24 |  |  | 0
Sri Lanka | M A K Prasanna dans@caa.lk | 0 | 0 |  |  | 0
Thailand | Mr. Karan Chantrong karan.c@caat.or.th | 62 | 58 | 58 | 10 | 72 | No | [7 empty] | 10 | 1 year | Jan 2020
Timor Leste |  |  | 5 |  |  | 0
Tonga | Tino Fuka tfuka@tongaairports.com | 8 | 8 |  |  | 0
Tuvalu |  | 2 | 2 |  |  | 0
Vanuatu | Mr. Paul Lennis paul.civa@vanuatu.com.vu | 13 | 13 |  |  | 0
Vietnam | Mr. Nguyen The Hung hungand@caa.gov.vn | 9 | 2 |  |  | 0
New Caledonia | Mr. Maxime Fournier maxime.fournier@aviation-civile.gouv.fr |  | 9 | 9 | 5 | 14 | Vanuatu & Fiji, if possible, New Zealand & Australia | [7 empty] | 1 |  | 20 Jun 2019
French Polynesia | Aurélie Laplane aurelie.laplane@aviation-civile-gouv.fr |  |  | 35 | 12 | 47 | No | [7 empty] | 2 |  | 18 Jul 2019
Wallis and Futuna Is. | Mr. Maxime Fournier maxime.fournier@aviation-civile.gouv.fr |  | 1 | 2 | 2 | 4
United States of America | Victoria Williams |  |  | 19 | 0 | 19 | NA | [7 empty] | NA |  | NA | The US does not intend to change chart identification for 6596 RNP APCH and 413 RNP AR procedures. The US will include PBN requirements box information on all new and amended approach procedures as routinely published.
Total |  | 1350 | 1755
Note on C8: Knowles, Ian: Data based on figures held by ICAO HQ - these need to be confirmed
Note on E10: Ha, HuHo: RNAV(GNSS) 586 RNAV(RNP) 67
Note on F12: Ha, HuHo: planned 1 RNP (AR)
Note on E15: Total 468 by 25 Apr 2019 RNP 151 RNAV(GNSS) 317
Note on F17: Ha, HuHo: Planned 3 RNP (AR)
Note on E24: Ha, HuHo: RNAV(GNSS) 38, RNAV(RNP) 55
Note on F28: Ha, HuHo: planned 20 RNP
Note on R28: Ha, HuHo: AIC will be issued in advance
Note on E32: Ha, HuHo: 8 RNP
Note on F32: Ha, HuHo: 28 RNP
Note on E34: Ha, HuHo: RNAV(GNSS) 3 RNAVRNP) 1
Note on F34: Ha, HuHo: Planned 4 RNP
Note on P34: Ha, HuHo: RNAV(GNSS) by Mar 2019 RNAV(RNP) by Jun 2019
Note on E35: Ha, HuHo: RNAV(GNSS) 106 RNAV(RNP) 10
Note on F35: Ha, HuHo: Approx. 10 RNAV(GNSS)
Note on E45: Ha, HuHo: RNAV(GNSS) 56 RNAV(RNP) 2
Note on F45: Ha, HuHo: RNAV(GNSS) 8 RNAV(RNP) 6 RNP 64 RNP (AR) 8
Note on H51: Ha, HuHo: New Zealand (Auckland), Australia (Brisbane, Sydney and Melbourne)
Note on R51: Ha, HuHo: 08/19 AIRAC cycle
Note on F52: Ha, HuHo: 2018 4, 2019 8
Note on R52: Ha, HuHo: AIRAC cycle 09/19
Note on E54: Ha, HuHo: RNAV(GNSS) 15 RNAV(RNP) 4 within APAC region

## Draft Reg'l Plan-State review
RNAV to RNP Chart Identification Change
Constraints
Regional Transition Plan | [9 empty] | # of charts changed |  |  |  |  | 1730
[10 empty] | Capacity Chart Service Provider |  |  |  |  | 180
Region: | APAC |  | To be used in conjunction with Circular 353 only | [6 empty] | Capacity Chart Service Provider adjusted |  |  |  |  | 120
[10 empty] | Required AIRAC Cycle: |  |  |  |  | 9.6111
Use the following data to develop a proposed regional slot for transition. Actual slot will be coordinated and allocated by the ICAO PBN Programme Office | [9 empty] | Required AIRAC Cycle adjusted: |  |  |  |  | 14.4167
[10 empty] | Regional Transition Plan no later than |  |  |  |  | Jun 2019
|  | AIRAC cycle dates: |  | https://www.nm.eurocontrol.int/RAD/common/airac_dates.html
| Figures below are filled automatically - do not change |  |  |  | Enter values here: |  |  |  |  | 2019 | [5 empty] | 2020
| Start Date | Sequence based on ready date | No. of Charts | Required number of Airac Cycles | Allocated AIRAC Cycle |  | Earliest Proposed Start Date | Latest Proposed Start Date | No. of AIRAC Cycle | Jul 18 | Aug 15 | Sep 12 | Oct 10 | Nov 07 | Dec 05 | Jan 02 | Jan 30 | Feb 27 | Mar 26 | Apr 23 | May 21 | Jun 18 | Jul 16 | Aug 13 | Sep 10 | Oct 08 | Nov 05 | State's comment
Afghanistan | 2019-10-10 | 27 | 6 | 1 |  |  | 2019-07-18 | 2020-06-18 | 1
Australia | 2019-08-15 | 32 | 653 | 18+ |  | 18 months |  |  | 18+ | [18 empty] | Follow own transiton schedule
Bangladesh | 2019-10-10 | 27 | 1 | 1 |  |  |  |  | 1 | [18 empty] | 5 RNP, 1 RNAV(GNSS)
Bhutan | 2019-10-10 | 27 | 3 | 1 |  |  |  |  | 1
Brunei Darussalam | 2020-06-18 | 1 | 2 | 1 |  |  |  |  | 1
Cambodia | 2020-02-27 | 16 | 5 | 1 |  |  |  |  | 1
China | 2019-07-18 | 36 | 317 | 18+ |  | Published RNP 151 | 11 Oct 2018 | 31 Dec 2020 | 18+ | [18 empty] | 151 RNP, 317 RNAV(GNSS)
Hong Kong, China | 2020-01-02 | 20 | 8 | 6 |  |  |  |  | 6
Macao, China | 2020-01-02 | 20 | 4 | 6 |  |  |  |  | 6
Taipei FIR | 2020-01-30 | 19 | 22 | 4 |  |  |  |  | 4
Cook Islands | 2020-03-26 | 10 | 15 | 3 |  |  |  |  | 3
Democratic Peoples Republic of Korea | 2019-08-15 | 32 | 4 | 1 |  |  |  |  | 1
Fiji | 2019-07-18 | 36 | 8 | 1 |  |  |  |  | 1
India | 2019-10-10 | 27 | 4 | 1 |  |  |  |  | 1
Indonesia | 2020-06-18 | 1 | 76 | 6 |  |  |  |  | 6
Japan | 2020-01-02 | 20 | 93 | 12+ |  | Published 25 GPS App |  |  | 12+ | [18 empty] | Follow own transition schedule
Kiribati | 2020-03-26 | 10 | 4 | 1 |  |  |  |  | 1
Lao Peoples' Democratic Republic | 2020-02-27 | 16 | 5 | 1 |  |  |  |  | 1
Malaysia | 2020-01-02 | 20 | 50 | 6 |  |  |  |  | 6
Maldives | 2019-07-18 | 36 | 16 | 1 |  |  |  |  | 1 | [18 empty] | Complete by May 2019
Marshall Islands | 2020-03-26 | 10 | 6 | 1 |  |  |  |  | 1
Micronesia | 2020-06-18 | 1 | 10 | 1 |  |  |  |  | 1
Mongolia | 2019-08-15 | 32 | 3 | 1 |  |  |  |  | 1
Myanmar | NA | #VALUE! | 0 | 0 |  | Implemented |  |  | 0 | [18 empty] | Implemented
Nauru | 2020-03-26 | 10 | 0 | 0 |  |  |  |  | 0
Nepal | 2019-07-18 | 36 | 4 | 2 |  |  |  |  | 2
New Zealand | 2019-07-18 | 36 | 126 | 18+ |  | progressive implementation |  |  | 18+ | [18 empty] | Follow own transition schedule
Pakistan | 2019-10-10 | 27 | 43 | 12 |  |  |  |  | 12
Palau | 2020-06-18 | 1 | 2 | 1 |  |  |  |  | 1
Papua New Guinea | 2020-06-18 | 1 | 2 | 1 |  | Published 15 GPS App |  |  | 1
Philippines | 2020-01-02 | 20 | 31 | 12 |  |  |  |  | 12
Republic of Korea | 2019-08-15 | 32 | 32 | 1 |  |  |  |  | 1
Samoa | 2020-03-26 | 10 | 5 | 1 |  |  |  |  | 1
Singapore | 2020-01-02 | 20 | 6 | 2 |  | implement anytime |  |  | 2
Solomon Islands | 2020-03-26 | 10 | 0 | 0 |  | Published 24 GPS App |  |  | 0
Sri Lanka | NA | #VALUE! | 0 | 0 |  | Implemented |  |  | 0 | [18 empty] | Implemented
Thailand | 2020-01-02 | 20 | 62 | 10 |  |  |  |  | 10
Timor Leste | 2020-06-18 | 1 | 5 | 1 |  |  |  |  | 1
Tonga | 2020-04-23 | 8 | 8 | 1 |  |  |  |  | 1
Tuvalu | 2020-05-21 | 7 | 2 | 1 |  |  |  |  | 1
Vanuatu | 2020-04-23 | 8 | 13 | 2 |  |  |  |  | 2
Vietnam | 2020-02-27 | 16 | 9 | 1 |  |  |  |  | 1
New Caledonia | 2019-07-18 | 36 | 9 | 1 |  |  |  |  | 1
French Polynesia | 2019-08-15 | 32 | 35 | 2 |  |  |  |  | 2
Wallis and Futuna Is. | 2019-07-18 | 37 | 2 | 1 |  |  |  |  | 1
United States of America | NA | #VALUE! | 19 | 0 |  |  |  |  | 0 | [18 empty] | No transition
1730
* China : Published PBN procedures are in domestic AIP and will not affect regional transition.
* USA : These is no intention to change chart title. US will include PBN requirement box in the chart.
* Austalia proposed to follow the triennial procedure validation cycle. If resources available, transition will be made in 18 months. Chart will be published quartly
Formulas:
Earliest Proposed Start Date = MIN([Start Date]:B58)
Latest Proposed Start Date = MAX([Start Date]:B58)
Note on G28: Ha, HuHo: Published GPS based approaches need to be redesigned to RNAV(GNSS), than will begin to transition.
Note on G39: Ha, HuHo: Implementation will follow IFP procedure periodic maintenance cycle. International airport first

## State response
Response received (AP154/18 (ATM), 20 Nov 2018)
No | States | Date | Action taken
1 | Maldives | Nov 22 | transition began effective on Jan 3 2019
2 | New Caledonia | Nov 26 | Slot adjusted (Wallis and Futuna Is.)
3 | Pakistan | Dec 12 | Accepted
4 | Singapore | Dec 13 | updated
5 | Australia | Dec 20 | provided opinion. Will discuss at PBNICG6
6 | Malaysia | Dec 20 | Updated
7 | ROK | Dec 27 | updated
8 | Thailand | Jan 3 | updated
9 | Macao, China | Jan 3 | updated
10 | Hong Kong China | Jan 4 | updated
11 | New Zealand | Jan 9 | Accepted
12 | USA | Jan 11 | No comment. Will not follow the APAC plan
13 | Nepal | Feb 12 | Accepted
14 | Sri Lanka | Feb 19 | Confirmed their information. Transition completed.
15 | Bangladesh | April 2 | Accepted
16 | China | April 5 | provided information